## Sheet1
Notes | ID | Complete By | Property | Type | Assigned To | Status | Priority | Comments | Last Updated Date
| 1277041 | 2025-01-24 12:44 | 06951 - CW Lake Underhill | Signage | EMPL Smith | In Progress | 30 Day | We need Center well parking lot assigned and identify for the health center as per agreement with Walmart (minimum 6 spaces). Please notice that the parking lots should be the closer to the health center main entrance. Our patients are 65 and walking long distance is an issue. Many have already reported that they can't find parking space that is close to the health center. | 1/24/2025 4:18 PM EST
| 1277970 | 2025-02-15 12:05 | 03685 - CV West Hillsborough | HVAC | VDR RSC Mechanical, Inc. | Acknowledged | P4-Routine | Please provide a quote to replace all 3 units | 2/3/2025 1:56 PM EST
| 1280739 | 2025-01-13 14:00 | 03619 - CV Plant City | Building Maintenance | EMPL ME Seebaran | Work Complete | P4-Routine | Stained ceiling tile in the breakroom. | 1/8/2025 2:15 PM EST
| 1280754 | 2025-01-10 16:42 | 05435 - CW OVIEDO | Building Maintenance | EMPL ME Barreto | Work Complete | P5-Low | Assemble shelf for providers office | 1/29/2025 11:39 AM EST
| 1287273 | 2025-01-09 16:27 | 06046 - CW WEST ORANGE | Building Maintenance | LL PSC Landlord (PSC Use Only) | Acknowledged | P3-Moderate | This is a child WO for 1280068 for the roof leak. LLD letter has been sent for the roof leak. | 1/30/2025 3:51 PM EST
| 1288329 | 2025-01-14 11:00 | 06678 - CV Winter Haven | Electrical | EMPL ME Seebaran | Work Complete | P3-Moderate | The fuse box has a fuse that has popped, and entire fuse is elevated above the rest around it. I wanted to ask if someone could come and check it out. It is the fuse for the provider offices on the second floor. | 2/6/2025 9:03 AM EST
| 1290587 | 2025-01-23 08:42 | 05212 - CW CASSELBERRY | Fire/Life Safety | VDR Academy Fire Life Safety LLC | Work Complete | P3-Moderate | AFLS dispatched a technician to this location on an annual fire extinguisher inspection. While on site the technician found (5) 5lb ABC fire extinguishers due for 6 year service in order to provide coverage | 2/4/2025 2:10 PM EST
| 1289037 | 2025-01-27 14:14 | 05435 - CW OVIEDO | Building Maintenance | EMPL ME Barreto | Work Complete | P5-Low | Request to assemble bookshelf for physician room | 1/24/2025 3:23 PM EST
| 1294089 | 2025-01-30 09:29 | 06088 - CV Pinellas Park | Electrical | HUM AV Support Team | In Progress | P3-Moderate | The TV in the Wellness room is not turning on. When you turn on the TV it shuts back off. This is a Child WO from WO 1289887. | 2/6/2025 10:36 AM EST
| 1294880 | 2025-01-30 14:11 | 06439 - CW Leesburg | Plumbing | VDR Virtue Construction and Design, LLC | Work Complete | P2-Urgent | Employee Bathrooms bubbled and it has come up the drains in the janitor closet. I spoke with Jeremiah Daniels, and he said someone will be out for plumbing, but we also need someone to clean the janitor closet, and we will need new brooms and mops. | 1/31/2025 7:20 AM EST
| 1293463 | 2025-01-30 14:15 | 06951 - CW Lake Underhill | Building Maintenance | EMPL Cerone | Acknowledged | P4-Routine | We need to hang and secure the lab pick up boxes outside the office entrance | 1/31/2025 2:31 PM EST
| 1293920 | 2025-01-31 11:09 | 06960 - CV Zephyrhills | Plumbing | EMPL Cerone | In Progress | P4-Routine | There is an existing small leak in the Domestic water backflow located in Room behind IT Room. Will open a WM work order | 2/6/2025 11:04 AM EST
| 1294504 | 2025-02-03 08:00 | 06088 - CV Pinellas Park | HVAC | VDR RSC Mechanical, Inc. | In Progress | P3-Moderate | RTU 3 has error codes and fault 28 showing on the VFD. Vendor is required to troubleshoot the unit. | 2/4/2025 2:10 PM EST
| 1294605 | 2025-02-03 08:50 | 06126 - CV Safety Harbor | Plumbing | LL PSC Landlord (PSC Use Only) | In Progress | P3-Moderate | Low water pressure in exam room 1 sink. Low water pressure in the toilet in the patient restroom. This is a child WO from WO 1290778. | 2/4/2025 3:41 PM EST
| 1297566 | 2025-02-04 10:44 | 05435 - CW OVIEDO | Plumbing | EMPL ME Barreto | Work Complete | P2-Urgent | One of the Back-office bathrooms is clogged. (Patient Bathroom) | 2/4/2025 11:25 AM EST
| 1294212 | 2025-02-04 14:00 | 06610 - CW Southchase | Building Maintenance | EMPL ME Barreto | Work Complete | P4-Routine | Stained ceiling tiles behind back door exit sign | 2/4/2025 1:40 PM EST
| 1294214 | 2025-02-04 14:00 | 02319 - CW West Vine | Building Maintenance | EMPL ME Seebaran | Work Complete | P4-Routine | Stained ceiling tile in activity center stained ceiling tile by exam room 22 in hallways | 2/4/2025 11:24 AM EST
| 1294219 | 2025-02-04 14:00 | 05227 - CW THE VILLAGES | Building Maintenance | VDR Virtue Construction and Design, LLC | Work Complete | P4-Routine | Electrical safety issues, ca needs a additional outlet installed in CA office. | 2/3/2025 9:59 AM EST
| 1294502 | 2025-02-05 08:00 | 02457 - EH Sarasota | Doors/Locks/Keys | VDR Virtue Construction and Design, LLC | Work Complete | P4-Routine | 3 of the office sliding doors are off the tracks and need to be reset. This is child work order for WO 1291749 | 2/4/2025 6:50 PM EST
| 1297731 | 2025-02-05 08:18 | 06439 - CW Leesburg | Plumbing | VDR Virtue Construction and Design, LLC | Work Complete | P2-Urgent | The toilet is back up and the floor drain in the janitor’s closet is bubbling up | 2/5/2025 2:12 PM EST
| 1294733 | 2025-02-05 11:22 | 06678 - CV Winter Haven | Doors/Locks/Keys | VDR GLMC Group, LLC | In Progress | P4-Routine | our doors are not handicap accesible in the sense that there is no functioning button to automatically open the doors. Pts have to wait or knock on the door for someone to come help open it for them if they are wheelchair bound. | 2/5/2025 8:58 AM EST
| 1297836 | 2025-02-05 12:33 | 05215 - CW HUNTER'S CREEK | HVAC | EMPL ME Seebaran | Work Complete | P2-Urgent | Air conditioner is not turning on (it is 75 degrees on Dr. Campbell's side of the building). When bringing the temp down the air unit is not turning on. | 2/5/2025 4:48 PM EST
| 1294730 | 2025-02-05 14:00 | 06678 - CV Winter Haven | Building Maintenance | EMPL ME Seebaran | Work Complete | P4-Routine | Stained ceiling tile in the men restroom on the second floor next to the waiting area. | 2/5/2025 4:59 PM EST
| 1295458 | 2025-02-05 14:00 | 06957 - CV St Petersburg | Fire/Life Safety | EMPL Cerone | In Progress | P3-Moderate | Walmart Site: CA contacted me to inform that all FE certifications have expired and need to be replaced. | 2/6/2025 11:04 AM EST
| 1297908 | 2025-02-05 15:02 | 03619 - CV Plant City | Pest Control | VDR Rentokil Steritech | Acknowledged | P2-Urgent | German roach activity found in MA station closest to the front of the building. | 2/5/2025 2:25 PM EST
| 1297972 | 2025-02-05 16:05 | 05211 - CW APOPKA | Pest Control | VDR Rentokil Steritech | Acknowledged | P2-Urgent | I found a roach in the cabinet kitchen | 2/5/2025 3:35 PM EST
| 1298073 | 2025-02-06 09:21 | 06076 - CW LONGWOOD | HVAC | EMPL ME Barreto | Work Complete | P2-Urgent | Please adjust the AC in lobby and lab as it is still cold in these areas. This is a child WO from 1297659. | 2/5/2025 5:12 PM EST
| 1295055 | 2025-02-06 11:27 | 03685 - CV West Hillsborough | HVAC | VDR Wilson & Company | Acknowledged | P4-Routine | current humidity levels hover around 65%, please provide an estimate for replacing the current units with appropriately sized units that match the required tonnage for the space. | 2/6/2025 10:39 AM EST
| 1297601 | 2025-02-06 13:10 | 06949 - CW Gateway Station | Plumbing | EMPL Cerone | In Progress | P3-Moderate | This is a follow up work order for the patient restroom toilet, still has not been repaired | 2/5/2025 1:40 PM EST
| 1295097 | 2025-02-06 13:16 | 06153 - CV Dunedin | Building Maintenance | EMPL ME Seebaran | Work Complete | P4-Routine | New provider name Kaitlyn Brown P.A. and decal with the PCP name needs to be hung on clinic door. This is a child WO from WO 1277478. | 2/5/2025 4:36 PM EST
| 1295113 | 2025-02-06 14:13 | 05211 - CW APOPKA | Building Maintenance | VDR Virtue Construction and Design, LLC | Work Complete | P4-Routine | Patient crashed mobility scooter into countertop in room causing the counter to un attach from the wall. | 2/6/2025 2:28 PM EST
| 1297746 | 2025-02-07 08:52 | 06153 - CV Dunedin | Pest Control | VDR Vast Electrical Contractors, Inc. | Work Complete | P3-Moderate | we are getting roaches again in the rooms | 2/5/2025 4:27 PM EST
| 1295384 | 2025-02-07 10:21 | 05227 - CW THE VILLAGES | Doors/Locks/Keys | EMPL ME Seebaran | Work Complete | P4-Routine | Janitorial closet which is in view of patients - door is not staying closed. | 2/5/2025 4:33 PM EST
| 1297796 | 2025-02-07 10:50 | 06957 - CV St Petersburg | Plumbing | EMPL ME Seebaran | Work Complete | P3-Moderate | Bathroom sink is spraying quickly when turned on, not leaking. This is causing sink to fill up and not drain. | 2/5/2025 4:56 PM EST
| 1298813 | 2025-02-07 13:51 | 05227 - CW THE VILLAGES | Doors/Locks/Keys | EMPL ME Seebaran | Work Complete | P2-Urgent | Front door again not locking - giving issues. I believe this door needs to be replaced ASAP. Office needs to be secured with no questions asked and lately this door has been giving many issues. | 2/6/2025 7:30 PM EST
| 1298814 | 2025-02-07 13:53 | 06153 - CV Dunedin | Plumbing | EMPL ME Seebaran | Work Complete | P2-Urgent | LADIES BATHROON LEAK UNDER THE SINK (SLOW LEAK ) | 2/7/2025 7:46 AM EST
| 1295513 | 2025-02-07 16:10 | 06680 - CV Lowry Park | Plumbing | EMPL ME Seebaran | Work Complete | P4-Routine | Toilet overflows when flushed. Also pls see faucet in exam room #1, which is leaking. Also hang hook for patient bags and jackets, in the patient bathroom next to the scales and lab. See images. | 2/4/2025 11:36 AM EST
| 1295028 | 2025-02-10 09:00 | 05758 - CW Millenia Admin | Building Maintenance | EMPL ME Barreto | Work Complete | P4-Routine | Stained ceiling tile in hallway by action 22 room, stained ceiling tile in conference room. Stained ceiling tile in back area by connect room 6. Please replace | 2/4/2025 11:28 AM EST
| 1295029 | 2025-02-10 09:00 | 06951 - CW Lake Underhill | Building Maintenance | EMPL Cerone | In Progress | P4-Routine | Stained ceiling tile in care team area. Please assess and replace | 2/5/2025 1:37 PM EST
| 1297525 | 2025-02-10 09:41 | 05215 - CW HUNTER'S CREEK | Doors/Locks/Keys | EMPL ME Seebaran | Work Complete | P4-Routine | Add door closure on the patient bathroom door in the lobby waiting area. | 2/6/2025 2:24 PM EST
| 1297568 | 2025-02-10 10:45 | 06153 - CV Dunedin | HVAC | VDR RSC Mechanical, Inc. | In Progress | P4-Routine | The AC is not working on the new side | 2/6/2025 9:48 AM EST
| 1297582 | 2025-02-10 11:36 | 06959 - CW Winter Garden | Building Maintenance | EMPL Cerone | In Progress | P4-Routine | Stained Ceiling tile in bathroom across from MA station, please replace. | 2/5/2025 1:42 PM EST
| 1297583 | 2025-02-10 11:38 | 05227 - CW THE VILLAGES | Building Maintenance | EMPL ME Seebaran | Work Complete | P4-Routine | The storage room marked for oxygen This door also needs grease on the hinges. Squeaks a lot. Also a stained ceiling tile is in this room | 2/5/2025 4:32 PM EST
| 1297588 | 2025-02-10 11:58 | 02319 - CW West Vine | Doors/Locks/Keys | VDR GLMC Group, LLC | In Progress | P4-Routine | This location has sypher locks on the same doors where the card readers are located. Please provide a count of the sypher locks and cost to replace with ADA level sets, and keyed to existing master system | 2/5/2025 7:35 AM EST
| 1297616 | 2025-02-10 14:01 | 02457 - EH Sarasota | Building Maintenance | EMPL ME Seebaran | Work Complete | P4-Routine | Found water in IT/Electrical Room, unsure if coming from mini-split or other as not in normal spot that has condensation from Mini-split. | 2/5/2025 4:54 PM EST
| 1297645 | 2025-02-10 14:12 | 06207 - Winter Haven | Building Maintenance | EMPL ME Seebaran | Work Complete | P4-Routine | Please assess and take picture of area where car hit the building. Report back to FM. | 2/4/2025 7:47 PM EST
| 1298524 | 2025-02-10 16:52 | 05207 - CW ALTAMONTE | Electrical | EMPL ME Seebaran | Work Complete | P3-Moderate | Lights in room 6 are out | 2/6/2025 2:30 PM EST
| 1297694 | 2025-02-11 08:00 | 06677 - CV North Lakeland | Elevator | VDR Thyssenkrupp Elevator | Acknowledged | P4-Routine | TK Elevator will provide and install a cab exhaust fan on the elevator(s) referenced above. This cab fan is specifically designed for elevators and engineered for maximum airflow distribution. Whenever the doors open, fresh air enters the cab from the climate-controlled hallways and stale air exits into the hoistway. | 2/5/2025 7:38 AM EST
| 1297697 | 2025-02-11 08:00 | 03685 - CV West Hillsborough | Building Maintenance | EMPL ME Seebaran | Work Complete | P4-Routine | Ca is requesting to add a thermometer on the lab wall as well as a Snellen Eye chart in the hallway for patients. | 2/4/2025 9:05 AM EST
| 1298623 | 2025-02-11 08:00 | 05208 - CW BVL | Electrical | EMPL ME Seebaran | Work Complete | P3-Moderate | There is a missing wall plate in the Care Team area near the oxygen tank storage room. | 2/6/2025 2:31 PM EST
| 1298624 | 2025-02-11 08:00 | 06951 - CW Lake Underhill | Building Maintenance | EMPL Cerone | In Progress | P3-Moderate | There is a stained ceiling located near the second MA station area by the skylight, Picture is attached with a red circle showing the area of concern. | 2/6/2025 11:02 AM EST
| 1297740 | 2025-02-11 08:29 | 05211 - CW APOPKA | HVAC | EMPL ME Barreto | Work Complete | P4-Routine | There is a leak in the IT room coming from the air. Water is coming out of the room | 2/5/2025 5:23 PM EST
| 1298757 | 2025-02-11 11:40 | 05483 - CV South Tampa | Lighting | VDR Vast Electrical Contractors, Inc. | Acknowledged | P3-Moderate | Theres a smart lighting fixture with a bad drive in center administrators' office. This is a child WO from WO 1298652. | 2/6/2025 11:40 AM EST
| 1297820 | 2025-02-11 11:45 | 05215 - CW HUNTER'S CREEK | Building Maintenance | EMPL ME Seebaran | Work Complete | P4-Routine | Please assess potential roof leak above biohazard room, inform FM with findings. | 2/5/2025 8:48 AM EST
| 1298776 | 2025-02-11 12:20 | 05215 - CW HUNTER'S CREEK | Lighting | EMPL ME Seebaran | Acknowledged | P3-Moderate | Light out in Dr. Leon care team area, located in back right of office once entering | 2/6/2025 1:23 PM EST
| 1297853 | 2025-02-11 14:00 | 06956 - CV New Port Richey | Building Maintenance | EMPL Cerone | In Progress | P4-Routine | Stained ceiling tile in exam room #2 and the exam room next to #2 that is not labeled. | 2/6/2025 11:10 AM EST
| 1298823 | 2025-02-11 14:02 | 06680 - CV Lowry Park | HVAC | EMPL Cerone | Acknowledged | P3-Moderate | Currently set to 74, reading is 77. System isn't responding to requested temperature. Also would like to request both thermostats be programmed and for covers to be placed. Thx | 2/6/2025 2:36 PM EST
| 1297869 | 2025-02-11 14:22 | 06153 - CV Dunedin | Kitchen/Cafe | HUM VDR Sodexo - INEZ ANN | In Progress | P4-Routine | needing water and coffee | 2/5/2025 12:10 PM EST
| 1298104 | 2025-02-12 09:25 | 06088 - CV Pinellas Park | Building Maintenance | EMPL ME Seebaran | Work Complete | P4-Routine | Blinds fell off in the lobby | 2/5/2025 4:35 PM EST
| 1298143 | 2025-02-12 09:58 | 05209 - CW CLERMONT | Building Maintenance | EMPL ME Barreto | Acknowledged | P4-Routine | Please replace all ceiling tiles from roof leak that was repaired. This is a child WO from 1293441. | 2/5/2025 9:58 AM EST
| 1298290 | 2025-02-12 11:35 | 06956 - CV New Port Richey | Plumbing | EMPL Cerone | In Progress | P4-Routine | Drains in floor needs attention. Center is smells of sewage and traps may have a malfunction. | 2/6/2025 11:10 AM EST
| 1298475 | 2025-02-12 15:35 | 06439 - CW Leesburg | Building Maintenance | EMPL ME Barreto | Acknowledged | P4-Routine | need to have Marco hang Bulletin board in CA's office and also White Board Stand put together. | 2/5/2025 3:37 PM EST
| 1298523 | 2025-02-12 16:51 | 05207 - CW ALTAMONTE | Building Maintenance | EMPL ME Seebaran | Work Complete | P4-Routine | Cabinet door broken in lobby | 2/6/2025 2:29 PM EST
| 1298642 | 2025-02-13 08:54 | 06955 - CV Land O Lakes | Building Maintenance | EMPL ME Seebaran | Acknowledged | P4-Routine | Per our vendor, we need to check if the breaker is on for our new sign out front. | 2/6/2025 9:09 AM EST
| 1298738 | 2025-02-13 10:52 | 04006 - HP Plant City | Building Maintenance | EMPL Cerone | Acknowledged | P4-Routine | would like to add a full sized refrigerator to the corner of the pharmacy near the IT box. (see Image 'serraview PC') in order to accomplish this, we would need to remove half or all of the cabinets/countertop in that section. We would need locks to be installed on a different cabinet (see video attached) We also request that we have a shelf (either millwork, wire rack or metal shelving) there (see attached photo 'IMG_1323') | 2/6/2025 2:36 PM EST
| 1298764 | 2025-02-13 11:52 | 06989 - CV Fowler | Doors/Locks/Keys | VDR GLMC Group, LLC | Acknowledged | P4-Routine | Replace Sypher locks, trip charge. | 2/6/2025 11:52 AM EST
| 1298778 | 2025-02-13 12:27 | 05215 - CW HUNTER'S CREEK | Building Maintenance | VDR CWS Mejia | Acknowledged | P4-Routine | Parking lot filled with garbage, requesting clean up services in parking lot | 2/6/2025 1:23 PM EST
| 1298780 | 2025-02-13 12:28 | 05215 - CW HUNTER'S CREEK | Plumbing | EMPL ME Seebaran | Acknowledged | P4-Routine | No hot water access in all sinks in center, repair service needed | 2/6/2025 1:22 PM EST
| 1298840 | 2025-02-13 14:48 | 03619 - CV Plant City | HVAC | EMPL ME Seebaran | In Progress | P4-Routine | HVAC water leak. CA also reported hard water smell in facility. | 2/6/2025 4:20 PM EST
| 1295471 | 2025-02-14 14:43 | 05208 - CW BVL | Building Maintenance | VDR Virtue Construction and Design, LLC | Work Complete | P5-Low | There are several areas within the clinic that are in need of paint touch-up, please provide pricing ONLY. | 2/6/2025 2:34 PM EST
| 1297997 | 2025-02-18 16:16 | 06949 - CW Gateway Station | Signage | EMPL ME Seebaran | Work Complete | P5-Low | Lab signage: 'No eating, drinking in this area' sign is posted in the Lab Area. 'No food or drink' sign is posted on lab refrigerator. 'Do not unplug Refrigerator' Please hang signage. | 2/6/2025 7:31 PM EST
| 1298518 | 2025-02-19 16:34 | 06207 - Winter Haven | Signage | VDR Fastsigns Pembroke Pines - Jim | Acknowledged | P5-Low | Pharmacy needs the following signs ordered/installed: harassment policy acknowledgement quarantined sign Equal Employment opportunity Policy Statement HD/USP 600 Section Sign | 2/7/2025 6:26 AM EST
| 1280067 | 2025-02-21 15:30 | 05227 - CW THE VILLAGES | FM MAC Clinical | VDR Fastsigns Pembroke Pines - Jim | Work Complete | MAC-P5 | Restroom by break room needs signs stating employee only restroom | 2/6/2025 9:59 AM EST
| 1291761 | 2025-02-25 11:24 | 06724 - CV Brandon | Furniture Moves/Adds/Changes (MAC) | EMPL Cline | In Progress | MAC-P3 | Kindly requesting someone with muscles to come move around some exam beds. They just need to be repositioned within the rooms to better suite the staff and patients safety of the set up. | 2/4/2025 11:35 AM EST
| 1290590 | 2025-03-03 08:46 | 06680 - CV Lowry Park | Building Maintenance | EMPL Cerone | In Progress | 30 Day | Per WO 1289459 a new logo floor mat is being requested. FM to place Grainger order. | 2/4/2025 7:22 AM EST
| 1291786 | 2025-03-04 11:28 | 06724 - CV Brandon | Coffee/Water/Food Service/Vending | HUM VDR Sodexo - INEZ ANN | Work Complete | 30 Day | Requesting an order (case) of sugar and creamer canisters. We are completely out. We received coffee after our move, but no canisters. Thank you. | 2/5/2025 5:00 PM EST
| 1293308 | 2025-03-06 10:56 | 02457 - EH Sarasota | Coffee/Water/Food Service/Vending | HUM VDR Sodexo - INEZ ANN | In Progress | 30 Day |  | 2/4/2025 9:49 AM EST
| 1295042 | 2025-03-06 11:11 | 02319 - CW West Vine | Furniture Moves/Adds/Changes (MAC) | EMPL PDS Lechtenberger | In Progress | MAC-P3 | We need a refrigerator removed from the office. | 2/4/2025 5:35 PM EST
| 1293310 | 2025-03-06 12:00 | 06955 - CV Land O Lakes | Building Maintenance | EMPL Cerone | In Progress | 30 Day | Per CA Request, For a double door size Conviva floor mat. 84515-06955 – Conviva Land O Lakes - 1563 Land O' Lakes Blvd, Lutz, FL 33549. | 2/4/2025 7:23 AM EST
| 1293333 | 2025-03-06 14:00 | 06155 - CV Palm River | Roads & Grounds | LL PSC Landlord (PSC Use Only) | In Progress | 30 Day | Please address the site landscaping, with particular attention to the trees. | 1/24/2025 7:53 AM EST
| 1294021 | 2025-03-07 15:41 | 05483 - CV South Tampa | Building Maintenance | EMPL Cerone | In Progress | 30 Day | CA is requesting a replacement Conviva rug for the clinic. | 2/4/2025 7:21 AM EST
| 1294740 | 2025-03-12 14:00 | 06678 - CV Winter Haven | Building Maintenance | EMPL Cerone | In Progress | 30 Day | Per CA request to have both Main entrance mat needs to be replaced. | 1/30/2025 12:25 PM EST
| 1295082 | 2025-03-13 12:28 | 02457 - EH Sarasota | Signage | EMPL ME Seebaran | Work Complete | 30 Day | New Provider names received for front door, need old removed and replaced with new | 2/5/2025 4:53 PM EST
| 1295099 | 2025-03-13 13:21 | 02457 - EH Sarasota | Signage | EMPL ME Seebaran | Work Complete | 30 Day | Need to ADD name of NEW provider to door of facility, the other name stays - Anaisis Diaz, APRN. This is a child WO from WO 1289208. | 2/5/2025 4:52 PM EST
| 1295632 | 2025-03-17 14:00 | 06677 - CV North Lakeland | Roads & Grounds | EMPL ME Seebaran | Acknowledged | 30 Day | CA has requested landscaping for the enclosed area that can only be accessed through the office, as there is no exterior entry. | 2/3/2025 9:51 AM EST
| 1297658 | 2025-03-17 15:00 | 06610 - CW Southchase | Electrical | VDR GLMC Group, LLC | Work Complete | 30 Day | sensor of the handicap to open the door is not working inside the office or outside. | 2/5/2025 7:37 AM EST
| 1297669 | 2025-03-17 15:45 | 03686 - CW Engelwood Park | Building Maintenance | VDR CWS Mejia | Acknowledged | 30 Day | Deep cleaning on floors needed before February 15th & 16th | 2/3/2025 4:10 PM EST
| 1297778 | 2025-03-18 10:14 | 06155 - CV Palm River | Signage | EMPL ME Seebaran | Work Complete | 30 Day | Provider Rosa needs her name on door, please install the signage that was delivered. | 2/6/2025 4:21 PM EST
| 1298511 | 2025-03-19 16:19 | 06439 - CW Leesburg | Audio Visual | HUM AV Support Team | Work Complete | 30 Day | Unable to connect to tv in activity center. Message in right side on screen stating : Network 4, Do you want to allow your PC to be discoverable by other PC's and devices on this network? We recommend allowing this on your home and work networks but not public ones. Yes or No I am not logged in on my pc and the tv remove does not allow me to access the message. It is as if another pc is logged in but I do not know where or who. I have asked the staff no one appears to be logged into the tv in the activity center. | 2/6/2025 9:50 AM EST
| 1298711 | 2025-03-20 10:37 | 04006 - HP Plant City | Audio Visual | HUM AV Support Team | Request to Cancel WO | 30 Day | would like to request a DUAL monitor arm for the pharmacy front counter- there is currently one monitor there. we would need the current POS monitor mounted on the arm. we have a new PC that is coming that will go on the other arm. | 2/6/2025 12:38 PM EST
| 1290767 | 2025-03-21 14:00 | 06088 - CV Pinellas Park | Furniture Moves/Adds/Changes (MAC) | EMPL Cline | In Progress | MAC-P5 | Per CA Order and install shelving in the activity room and Place a cabinet similar to the specified type under the front desk table for filing purposes. Please see attachment for reference. | 2/5/2025 9:49 AM EST
| 1293979 | 2025-03-25 12:06 | 06948 - CW Poinciana | FM MAC Clinical | EMPL ME Barreto | Work Complete | MAC-P5 | build cabinet for u/s room | 2/5/2025 4:39 PM EST
| 1295045 | 2025-02-07 11:14 | 02319 - CW West Vine | Furniture Moves/Adds/Changes (MAC) | EMPL PDS Lechtenberger | In Progress | MAC-P5 | I need 7 chairs for patient for our Cardiology area within market portfolio. | 2/4/2025 5:35 PM EST
| 1124982 | N/A | 06610 - CW Southchase | Portfolio Change | VDR Rentokil Steritech | Acknowledged | No SLA | Please add annual PO as quoted below: Annual Cost: $684 Monthly Cost: $57 Services to begin on 4/29/24. Point of contact in regards to any questions about initial service: Abigail Corbett 407-438-5858 2nd point of contact in case Bill does not answer: Matthew Murray (Project Manager) (407)755-9049 | 1/2/2025 2:32 PM EST
| 1258062 | N/A | 06960 - CV Zephyrhills | Portfolio Change | VDR CWS Mejia | Acknowledged | No SLA | Please add janitorial services for this location as quoted below: Service: Nightly Cleaning (5x per week) Janitorial Services: $1,751.22 + applicable tax Consumables: $220.36 + applicable tax Total Monthly Cost: $1,971.58 + applicable tax Regular Nightly Cleaning Services will begin effective in late November 2024. Helena Cauchon (PM) will confirm the exact start date as soon as she has more information. | 1/2/2025 2:32 PM EST
| 1280215 | N/A | 06990 - CV Hanley Activ | Non-Recurring | VDR GLMC Group, LLC | WO/PO Approval Pending | No SLA | Rekey entire site with the following key program 1 master key opens all doors 10 keys that open only front and back doors 2 keys that open front back / doors + janitorial closet 2 keys that open front / back doors and IT room | 1/23/2025 3:38 PM EST
| 1280216 | N/A | 06991 - CC Hanley Dental | Non-Recurring | VDR GLMC Group, LLC | WO/PO Approved | No SLA | Rekey entire site with the following key program 1 master key opens all doors 10 keys that open only front and back doors 2 keys that open front back / doors + janitorial closet 2 keys that open front / back doors and IT room | 2/3/2025 5:28 PM EST
| 1280217 | N/A | 06992 - CC Hanley Acc | Non-Recurring | VDR GLMC Group, LLC | WO/PO Approval Pending | No SLA | Rekey entire site with the following key program 1 master key opens all doors 10 keys that open only front and back doors 2 keys that open front back / doors + janitorial closet 2 keys that open front / back doors and IT room | 1/23/2025 3:41 PM EST
| 1280219 | N/A | 06993 - CC Hanley 2 | Non-Recurring | VDR GLMC Group, LLC | WO/PO Approval Pending | No SLA | Rekey entire site with the following key program 1 master key opens all doors 10 keys that open only front and back doors 2 keys that open front back / doors + janitorial closet 2 keys that open front / back doors and IT room | 1/23/2025 3:42 PM EST
| 1280220 | N/A | 06994 - CC Hanley | Non-Recurring | VDR GLMC Group, LLC | WO/PO Approval Pending | No SLA |  | 1/23/2025 3:44 PM EST
| 1280221 | N/A | 07010 - CV E Palm River | Non-Recurring | VDR GLMC Group, LLC | WO/PO Approval Pending | No SLA | Rekey entire site with the following key program 1 master key opens all doors 10 keys that open only front and back doors 2 keys that open front back / doors + janitorial closet 2 keys that open front / back doors and IT room | 1/23/2025 3:59 PM EST
| 1280222 | N/A | 06975 - CC Pinellas Park | Non-Recurring | VDR GLMC Group, LLC | WO/PO Approval Pending | No SLA | Rekey entire site with the following key program 1 master key opens all doors 10 keys that open only front and back doors 2 keys that open front back / doors + janitorial closet 2 keys that open front / back doors and IT room | 1/23/2025 3:54 PM EST
| 1280224 | N/A | 06976 - CC Plant City | Non-Recurring | VDR GLMC Group, LLC | WO/PO Approval Pending | No SLA | Rekey entire site with the following key program 1 master key opens all doors 10 keys that open only front and back doors 2 keys that open front back / doors + janitorial closet 2 keys that open front / back doors and IT room | 1/23/2025 3:58 PM EST
| 1280225 | N/A | 07059 - CC Plant City Acc | Non-Recurring | VDR GLMC Group, LLC | WO/PO Approval Pending | No SLA | Rekey entire site with the following key program 1 master key opens all doors 10 keys that open only front and back doors 2 keys that open front back / doors + janitorial closet 2 keys that open front / back doors and IT room | 1/23/2025 3:47 PM EST
| 1280424 | N/A | 03686 - CW Engelwood Park | Non-Recurring | VDR Wilson & Company | WO/PO Approved | No SLA | Replace some areas of the LVT flooring in full and fill gaps, and clean glue in other areas. This flooring replacement work includes moisture mitigation sealer and application of RH 99 + Adhesive be used per the new standards. Estimate is attached. | 2/3/2025 4:36 PM EST
| 1286745 | N/A | 06957 - CV St Petersburg | Portfolio Change | VDR CWS Mejia | Acknowledged | No SLA | Please add janitorial services for this location as quoted below: Services: Nightly cleaning (5x/week) Monthly Janitorial Cost: $1,885.20 + applicable tax Monthly Consumables: $378.04 + applicable tax Total Monthly Cost: $2,263.24 + applicable tax Regular Nightly Cleaning Services will begin effective 2/3/25 | 1/3/2025 10:15 AM EST
| 1287076 | N/A | 06724 - CV Brandon | Security | HUM Humana Physical Security Operations | Request Approval for Reclassification | No SLA | The alarm/phone system is pinging 911 dispatch. Local Sherriff Officer have been sent to ensure everyone safety. After they arrive, the number that pinging their system is 813-657-3137. This number is not associated with Conviva or staff but is pinging from this building. This has happened twice today and on multiple occasions last week. Conviva has recently move into this existing building. There is a malfunction. | 1/3/2025 4:05 PM EST
| 1287087 | N/A | 07000 - CC Lakeland | Non-Recurring | VDR GLMC Group, LLC | WO/PO Approval Pending | No SLA | Facility re-key revised scope is exterior doors, IT closet, and any room that PHI or paper medical records are stored in, or any pharmacy rooms if there is one. Also note that the keypad locks need to be disconnected. | 1/23/2025 3:55 PM EST
| 1287088 | N/A | 07008 - CW Azalea | Non-Recurring | VDR GLMC Group, LLC | WO/PO Approval Pending | No SLA | Facility re-key revised scope is exterior doors, IT closet, and any room that PHI or paper medical records are stored in, or any pharmacy rooms if there is one. Also note that the keypad locks need to be disconnected. | 1/23/2025 3:45 PM EST
| 1287089 | N/A | 07009 - CC Palm River | Non-Recurring | VDR GLMC Group, LLC | WO/PO Approval Pending | No SLA | Facility re-key revised scope is exterior doors, IT closet, and any room that PHI or paper medical records are stored in, or any pharmacy rooms if there is one. Also note that the keypad locks need to be disconnected. | 1/23/2025 3:57 PM EST
| 1287090 | N/A | 07011 - CC PalmRiver7452 | Non-Recurring | VDR GLMC Group, LLC | WO/PO Approved | No SLA | Facility re-key revised scope is exterior doors, IT closet, and any room that PHI or paper medical records are stored in, or any pharmacy rooms if there is one. Also note that the keypad locks need to be disconnected. | 1/28/2025 2:09 PM EST
| 1287091 | N/A | 06981 - CV Winter Haven 2 | Non-Recurring | VDR GLMC Group, LLC | WO/PO Approval Pending | No SLA | Facility re-key revised scope is exterior doors, IT closet, and any room that PHI or paper medical records are stored in, or any pharmacy rooms if there is one. Also note that the keypad locks need to be disconnected. | 1/23/2025 4:02 PM EST
| 1287271 | N/A | 03619 - CV Plant City | Medical Equipment | EMPL Preciado | In Progress | No SLA | CA Denise Campis is looking for a height adjustable phlebotomy chair, with 2 arm rests and no vile box Her current chair is too short for their lab assistant to use, causing back pain | 1/31/2025 1:07 PM EST
| 1287280 | N/A | 04006 - HP Plant City | Non-Recurring | VDR Virtue Construction and Design, LLC | WO/PO Approved | No SLA | Need to remove glass and install new shutters per Pharmacist request | 1/27/2025 10:59 AM EST
| 1288364 | N/A | 03619 - CV Plant City | Security | HUM Humana Physical Security Operations | Acknowledged | No SLA | On 11/22/24 after noon and before 5pm one of our provider's cars was spray painted. Can someone look at the cameras to see who did this? The provider does not want to press charges at this time as she was able to remove the spray paint without damaging her car. The same initials are spray painted on the fence behind our center as well. There is a camera on that side of the building pointing toward the area where the car was parked. Please see attached photos. | 1/9/2025 12:25 PM EST
| 1288478 | N/A | 06999 - CC Hudson | Non-Recurring | VDR GLMC Group, LLC | WO/PO Declined | No SLA | Rekey entire site with the following key program 1 master key opens all doors 10 keys that open only front and back doors 2 keys that open front back / doors + janitorial closet 2 keys that open front / back doors and IT room | 1/24/2025 3:23 PM EST
| 1288479 | N/A | 07058 - CC Hudson Acc | Non-Recurring | VDR GLMC Group, LLC | WO/PO Approved | No SLA | Rekey entire site with the following key program 1 master key opens all doors 10 keys that open only front and back doors 2 keys that open front back / doors + janitorial closet 2 keys that open front / back doors and IT room | 1/28/2025 2:09 PM EST
| 1289066 | N/A | 05224 - CW POINCIANA | Non-Recurring | VDR BluSky Restoration Contractors - Christina | WO/PO Approved | No SLA | The dumpster has syringes and other trash that needs to be cleaned up around the dumpster enclosure. | 2/3/2025 5:25 PM EST
| 1293956 | N/A | 05435 - CW OVIEDO | Janitorial | VDR CWS Mejia | In Progress | No SLA | Janitorial is not properly cleaning the floor. There is dirt and hair early in the morning, reception area is not being vacuumed | 1/27/2025 10:48 AM EST
| 1294170 | N/A | 06677 - CV North Lakeland | Non-Recurring | VDR Thyssenkrupp Elevator | WO/PO Approved | No SLA | VENDOR WILL FURNISH AND INSTALL A DOOR LOCK MONITORING SYSTEM TO BRING ELEVATOR UP TO CODE. PER LEASE ALL MAINTENANCE IS TENANTS RESPONSIBILITIES | 1/31/2025 4:39 PM EST
| 1294473 | N/A | 03619 - CV Plant City | Events | VDR CWS Olivares | In Progress | No SLA | Center requires a deep clean on 2/20/25 in preparation for a commercial shoot to take place here on 2/22/25. | 1/29/2025 8:16 AM EST
| 1294705 | N/A | 06678 - CV Winter Haven | Shredding/Document Disposal | HUM VDR Iron Mountain | Acknowledged | No SLA | we need to obtain a document that was discarded by accident. It is an abnormal EKG and it is imperative to patients health. The EKG machine did not save a copy. | 1/29/2025 1:08 PM EST
| 1297751 | N/A | 06153 - CV Dunedin | Medical Equipment | EMPL Preciado | Acknowledged | No SLA | Urinalysis MAchine | 2/4/2025 9:52 AM EST
| 1297761 | N/A | 06610 - CW Southchase | Medical Equipment | EMPL ME Barreto | Work Complete | No SLA | Wheelchair scale doesn't turn on. There must be some cables missing | 2/5/2025 4:57 PM EST
| 1297910 | N/A | 06954 - CV Hudson | Events | EMPL Riebe | Acknowledged | No SLA | Landlord approval needed for April 22nd, 2025 Grand Opening event at Conviva Hudson. Also, need approval from the city and to request any permits if necessary to host the event. Proposed event setup attached. | 2/4/2025 3:38 PM EST
| 1298429 | N/A | 05211 - CW APOPKA | Janitorial | VDR CWS Mejia | In Progress | No SLA | To Whom It May Concern: My assumption is that the cleaning company (in the evening) mops, sweeps and cleans the mirrors (in addition to emptying out the trash) on a routine basis at the activity center. In the past 6 months the quality of the cleaning in the activity center portion of the building is continuing to decline. A few examples are as follows: - the mirrors (despite leaving notes to kindly wipe down) haven''t been touched in months; - front glass door entrance still had streaks from the last time I cleaned it. I don''t think they have ever been clean. - the floors haven''t been moped since I last put in a work order. - tables nor chairs are typically never wiped down If the duties I''ve stated above are outside of the responsibilities of the cleaning crew, kindly let me know so I can find the appropriate avenues to have these items addressed by the proper department. Thanks in advance for your time | 2/5/2025 8:32 PM EST
| 1298427 | N/A | 06088 - CV Pinellas Park | Janitorial | VDR CWS Mejia | Work Complete | No SLA | Request to Please address Women lobby restroom toilet. | 2/6/2025 6:59 AM EST
| 1298775 | N/A | 05215 - CW HUNTER'S CREEK | Security | HUM Humana Physical Security Operations | Acknowledged | No SLA | Front door secuirty sensor seems to trip at random points, all three entrances door magnet space needs to be evaluated. | 2/6/2025 1:22 PM EST
| 1298441 | N/A | 03686 - CW Engelwood Park | Vendor Escort | EMPL ME Barreto | Work Complete | No SLA | Please provide an escort for the flooring materials being delivered 2./6/25 @ 4:30PM. These will be placed in room 16 per the CA. | 2/6/2025 7:59 PM EST